## export - 2023-06-28T100116.389
PO Number | Item No | Supplier Item | Item Description | Due Date | Quantity Ordered | Quantity Shipped | Quantity Received | PENDING | UOM | Ship-To Location | Material Status | Transport details
IND7276437 | N39-PVCSPIRAL9 | N39-PVCSPIRAL9 | 9 PVC SPIRAL SLEEVE 9 MM ( COIL 30 MTR) | 2023-01-02 08:30 | 10 | 0 | 0 | 10 | Each | IF2_LOC_FS2 | yet to place order from kalika
IND7276437 | N31PGBUTOOL137 | N31PGBUTOOL137 | Normal Plier 1621-6, 165 MM TAPARIA | 2023-01-02 08:30 | 5 | 0 | 0 | 5 | Each | IF2_LOC_FS2 | order to oem
IND7276437 | N71-DOUBLETAPE2 | N71-DOUBLETAPE2 | Cloth Tape Double Sided Adhesive (2 Inch) 50mm | 2023-01-02 08:30 | 12 | 0 | 0 | 12 | Each | IF2_LOC_FS2 | dispatch from oem
IND7276437 | N57WELDINGROD05 | N57WELDINGROD05 | MS TO MS WELDING ROD MANGALAM MAKE, 2.5 MM MAKE: MANGALAM | 2023-01-02 08:30 | 1440 | 0 | 837 | 603 | Each | IF2_LOC_FS2 | ready to dispatch
IND7276437 | N37-2IN1SCREWDRIVER | N37-2IN1SCREWDRIVER | TAPARIA 803-55MM REVERSIBLE 2IN 1 SCREW DRIVER | 2023-01-02 08:30 | 5 | 0 | 0 | 5 | Each | IF2_LOC_FS2 | out for delivery
IND7306470 | N43SPRAYBOTTLE06 | N43SPRAYBOTTLE06 | SPRAY BOTTLE SIZE 200 ML | 2023-02-01 12:30 | 40 | 0 | 0 | 40 | Each | IF2_LOC_FS2
IND7306470 | N39EG-009-0073 | N39EG-009-0073 | CRC 5103 CO-CONTACT CLEANER | 2023-02-01 12:30 | 200 | 0 | 81 | 119 | Each | IF2_LOC_FS2
IND7317139 | N39-DURACELLD | N39-DURACELLD | DURACELL TYPE D TYPE BIG SIZE | 2023-02-13 04:30 | 18 | 0 | 12 | 6 | Each | IF2_LOC_FS2
IND7331516 | N31MEM01221 | N31MEM01221 | MEM-NOZ-OP10-Inventory Item-IN6.037.210HM04-S-E11990 s.c. special boring bar 5/6mm incl. TiAlN-coating Drawing No.: 022-800-01017 MOQ 30 Nos. Make TTC | 2023-02-27 08:30 | 50 | 0 | 0 | 50 | Each | IF2_LOC_FS2
IND7345772 | N69SHOESTIGERLEO | N69SHOESTIGERLEO | SAFETY SHOES (SINGLE DENSITY) MALLCOM MAKE | 2023-03-12 04:30 | 160 | 0 | 142 | 18 | Each | IF2_LOC_FS2
IND7347319 | N3112SHI301000 | N3112SHI301000 | Make Atom Precision Tail stock female half center CFS import from USA | 2023-03-14 04:30 | 10 | 0 | 2 | 8 | Each | IF2_LOC_FS2
IND7399284 | N3112SHI301000 | N3112SHI301000 | Make Atom Precision Tail stock female half center CFS import from USA | 2023-05-08 12:30 | 10 | 0 | 0 | 10 | Each | IF2_LOC_FS2
IND7411526 | N50POLY46X33X43 | N50POLY46X33X43 | Poly Bag size- 46 x 33 x 43 INCH 75 Nmicron | 2023-05-19 08:30 | 600 | 0 | 285 | 315 | Each | IF2_LOC_FS2
IND7432313 | N3112SHI201004 | N3112SHI201004 | Needle Grinding wheel Match CXY220K7V104 (72) 570 X 32 X 254 | 2023-06-12 08:31 | 3 | 0 | 0 | 3 | Each | IF2_LOC_FS2
IND7432313 | N3112SHI201005 | N3112SHI201005 | Needle Grinding Wheel Tip CXY220K7V104 (72) 570 X 55 X 254 | 2023-06-12 08:31 | 3 | 0 | 0 | 3 | Each | IF2_LOC_FS2
IND7445773 | N69PC-001-0094 | N69PC-001-0094 | TACK RAG (FOR PAINTING) | 2023-06-24 12:30 | 10000 | 0 | 0 | 10000 | Each | IF2_LOC_FS2

## Sheet1
Not Yet initiated
Next delivery
Delivered